## Column changes
Last activity date & time | Who made the change? | Item's name | Name | From | To | Total time diff (minutes) | Month | Group name | Item creation date & time | Type
05/04/2025 23:55:51 | Aya Amjad | continue reading from the last position at the pdf | Status |  | Done | 0 | April | test | 05/04/2025 23:55:51 | color
05/04/2025 23:55:17 | Aya Amjad | chat | Status |  | Done | 37527 | April | Planning | 05/04/2025 23:55:17 | color
05/04/2025 23:55:12 | Aya Amjad | connect flutter and python(http) | Status |  | Done | 0 | April | Planning | 05/04/2025 23:55:12 | color
05/04/2025 23:38:25 | Noor saleh | highlight | Status | Working on it | Stuck | 6007 | April | Planning | 05/04/2025 23:38:25 | color
05/04/2025 23:38:20 | Noor saleh | chat(image,text) | Status | Working on it | Done | 23478 | April | Planning | 05/04/2025 23:38:20 | color
05/04/2025 23:38:17 | Noor saleh | Summary | Status | Working on it | Done | 24588 | April | Planning | 05/04/2025 23:38:17 | color
02/04/2025 19:50:19 | Noor saleh | continue reading from the last position at the pdf | Status | Working on it | Done | 62 | April | Planning | 02/04/2025 19:50:19 | color
02/04/2025 18:47:59 | Noor saleh | continue reading from the last position at the pdf | Owner |  | Noor saleh | 0 | April | Planning | 02/04/2025 18:47:59 | multiple-person
02/04/2025 19:50:19 | Noor saleh | continue reading from the last position at the pdf | Status |  | Working on it | 0 | April | Planning | 02/04/2025 18:47:56 | color
02/04/2025 0:40:48 | Aya Amjad | name in main screen | Status |  | Done | 0 | April | test | 02/04/2025 0:40:48 | color
02/04/2025 0:40:45 | Aya Amjad | name and image email | Status |  | Done | 0 | April | test | 02/04/2025 0:40:45 | color
02/04/2025 0:40:34 | Aya Amjad | image and name email sign in | Status |  | Done | 469 | April | Planning | 02/04/2025 0:40:34 | color
01/04/2025 22:47:35 | Aya Amjad | chatbot | Status | Working on it |  | 0 | April | test | 01/04/2025 22:47:35 | color
01/04/2025 22:47:35 | Aya Amjad | chatbot | Status |  | Working on it | 0 | April | test | 01/04/2025 22:47:24 | color
01/04/2025 22:09:30 | Aya Amjad | no files yet | Status |  | Done | 0 | April | test | 01/04/2025 22:09:30 | color
01/04/2025 22:09:23 | Aya Amjad | not files yet | Status |  | Done | 0 | April | Planning | 01/04/2025 22:09:23 | color
01/04/2025 21:27:08 | Aya Amjad | design text Library | Status |  | Done | 0 | April | Planning | 01/04/2025 21:27:08 | color
01/04/2025 21:26:09 | Aya Amjad | search word in file | Status |  | Done | 0 | April | test | 01/04/2025 21:26:09 | color
01/04/2025 21:25:02 | Aya Amjad | modify search file | Status |  | Done | 0 | April | Planning | 01/04/2025 21:25:02 | color
01/04/2025 19:30:49 | Noor saleh | highlight | Owner |  | Noor saleh | 0 | April | Planning | 01/04/2025 19:30:49 | multiple-person
05/04/2025 23:38:25 | Noor saleh | highlight | Status | Done | Working on it | 3 | April | Planning | 01/04/2025 19:30:45 | color
05/04/2025 23:38:25 | Noor saleh | highlight | Status |  | Done | 0 | April | Planning | 01/04/2025 19:26:57 | color
01/04/2025 17:12:52 | Noor saleh | image and name email sign in | Owner | Noor saleh |  | 3811 | April | Planning | 01/04/2025 17:12:52 | multiple-person
02/04/2025 0:40:34 | Noor saleh | image and name email sign in | Status | Done |  | 2433 | April | Planning | 01/04/2025 16:50:44 | color
02/04/2025 0:40:34 | Noor saleh | image and name email sign in | Status | Working on it | Done | 59 | March | Planning | 31/03/2025 0:17:32 | color
30/03/2025 23:57:27 | Aya Amjad | bookmark | Status |  | Done | 0 | March | test | 30/03/2025 23:57:27 | color
02/04/2025 0:40:34 | Noor saleh | image and name email sign in | Status | On Hold | Working on it | 1296 | March | Planning | 30/03/2025 23:18:27 | color
30/03/2025 21:46:54 | Aya Amjad | details page | Status |  | Done | 0 | March | test | 30/03/2025 21:46:54 | color
30/03/2025 21:45:15 | Aya Amjad | to do list | Status |  | Done | 0 | March | test | 30/03/2025 21:45:15 | color
02/04/2025 0:40:34 | Noor saleh | image and name email sign in | Status | Future steps | On Hold | 0 | March | Planning | 30/03/2025 1:41:29 | color
02/04/2025 0:40:34 | Noor saleh | image and name email sign in | Status | On Hold | Future steps | 0 | March | Planning | 30/03/2025 1:41:23 | color
02/04/2025 0:40:34 | Noor saleh | image and name email sign in | Status |  | On Hold | 0 | March | Planning | 30/03/2025 1:41:10 | color
01/04/2025 17:12:52 | Noor saleh | image and name email sign in | Owner |  | Noor saleh | 0 | March | Planning | 30/03/2025 1:41:07 | multiple-person
30/03/2025 1:26:16 | Noor saleh | Book mark | Status | Working on it | Done | 254 | March | Planning | 30/03/2025 1:26:16 | color
29/03/2025 22:02:37 | Aya Amjad | logout | Status |  | Done | 0 | March | test | 29/03/2025 22:02:37 | color
29/03/2025 22:02:25 | Aya Amjad | home | Status |  | Done | 0 | March | test | 29/03/2025 22:02:25 | color
29/03/2025 22:02:19 | Aya Amjad | settting | Status |  | Done | 0 | March | test | 29/03/2025 22:02:19 | color
29/03/2025 22:01:48 | Aya Amjad | search title file | Status |  | Done | 0 | March | test | 29/03/2025 22:01:48 | color
29/03/2025 22:00:44 | Aya Amjad | delete fie | Status |  | Done | 0 | March | test | 29/03/2025 22:00:44 | color
29/03/2025 22:00:41 | Aya Amjad | translate | Status |  | Done | 0 | March | test | 29/03/2025 22:00:41 | color
29/03/2025 22:00:38 | Aya Amjad | notes | Status |  | Done | 0 | March | test | 29/03/2025 22:00:38 | color
29/03/2025 22:00:35 | Aya Amjad | add file | Status |  | Done | 0 | March | test | 29/03/2025 22:00:35 | color
29/03/2025 22:00:32 | Aya Amjad | forget password | Status |  | Done | 0 | March | test | 29/03/2025 22:00:32 | color
29/03/2025 22:00:29 | Aya Amjad | sign up | Status |  | Done | 0 | March | test | 29/03/2025 22:00:29 | color
29/03/2025 22:00:26 | Aya Amjad | sign in | Status |  | Done | 0 | March | test | 29/03/2025 22:00:26 | color
29/03/2025 22:00:24 | Aya Amjad | welcom | Status |  | Done | 0 | March | test | 29/03/2025 22:00:24 | color
29/03/2025 21:38:38 | Noor saleh | translate copy text | Owner |  | Aya Amjad | 0 | March | Planning | 29/03/2025 21:38:38 | multiple-person
29/03/2025 21:38:30 | Noor saleh | Book mark | Owner |  | Noor saleh | 0 | March | Planning | 29/03/2025 21:38:30 | multiple-person
30/03/2025 1:26:16 | Noor saleh | Book mark | Status |  | Working on it | 0 | March | Planning | 29/03/2025 21:11:41 | color
29/03/2025 21:11:36 | Aya Amjad | translate copy text | Status |  | Done | 0 | March | Planning | 29/03/2025 21:11:36 | color
29/03/2025 21:11:19 | Noor saleh | app book reader | Subitems | delete the file, search for the file name, pdf saving and deleting the lines and highliting | add bookmark, delete the file, search for the file name, pdf saving and deleting the lines and highliting | 20587 | March | Planning | 29/03/2025 21:11:19 | subtasks
28/03/2025 21:59:34 | Aya Amjad | search | Status |  | Done | 0 | March | Planning | 28/03/2025 21:59:34 | color
20/03/2025 17:44:07 | Noor saleh | package to explain users | Timeline | 2024-10-24 - 2024-10-30 |  | 0 | March | Planning | 20/03/2025 17:44:07 | timerange
20/03/2025 17:44:01 | Noor saleh | package to explain users | Status | Done |  | 0 | March | Planning | 20/03/2025 17:44:01 | color
20/03/2025 16:19:49 | Noor saleh | chat(image,text) | Subitems |  | get API | 0 | March | Planning | 20/03/2025 16:19:49 | subtasks
05/04/2025 23:38:20 | Noor saleh | chat(image,text) | Status |  | Working on it | 0 | March | Planning | 20/03/2025 16:19:31 | color
05/04/2025 23:38:17 | Noor saleh | Summary | Status |  | Working on it | 0 | March | Planning | 19/03/2025 21:50:04 | color
19/03/2025 21:49:14 | Noor saleh | Summary | Subitems |  | Api may need lo'a google cloud for API gemini | 0 | March | Planning | 19/03/2025 21:49:14 | subtasks
19/03/2025 12:33:27 | Noor saleh | Translate | Subitems | make both text field can do copy and pastt | see if we can add voise read the texr, make both text field can do copy and pastt | 0 | March | Planning | 19/03/2025 12:33:27 | subtasks
19/03/2025 12:33:27 | Noor saleh | Translate | Subitems |  | make both text field can do copy and pastt | 0 | March | Planning | 19/03/2025 12:32:58 | subtasks
15/03/2025 15:43:16 | Aya Amjad | Translate | Status | Working on it | Done | 101 | March | Planning | 15/03/2025 15:43:16 | color
29/03/2025 21:11:19 | Noor saleh | app book reader | Subitems | delete the file, search for the file name | pdf saving and deleting the lines and highliting, delete the file, search for the file name | 773 | March | Planning | 15/03/2025 14:03:53 | subtasks
15/03/2025 15:43:16 | Noor saleh | Translate | Status |  | Working on it | 1226 | March | Planning | 15/03/2025 14:02:01 | color
29/03/2025 21:11:19 | Noor saleh | app book reader | Subitems | delete the file | search, delete the file | 635 | March | Planning | 15/03/2025 1:10:28 | subtasks
15/03/2025 1:10:05 | Noor saleh | to do list | Status | Working on it | Done | 454 | March | Planning | 15/03/2025 1:10:05 | color
14/03/2025 17:35:14 | Aya Amjad | app book store | Status |  | Done | 0 | March | Planning | 14/03/2025 17:35:14 | color
15/03/2025 1:10:05 | Aya Amjad | to do list | Status |  | Working on it | 0 | March | Planning | 14/03/2025 17:35:07 | color
15/03/2025 15:43:16 | Aya Amjad | Translate | Status | Working on it |  | 5467 | March | Planning | 14/03/2025 17:35:03 | color
14/03/2025 17:34:59 | Aya Amjad | Note | Status |  | Done | 0 | March | Planning | 14/03/2025 17:34:59 | color
29/03/2025 21:11:19 | Noor saleh | app book reader | Subitems |  | delete the file | 0 | March | Planning | 14/03/2025 14:34:45 | subtasks
14/03/2025 14:34:37 | Noor saleh | Notpade | Subitems | update the note | delete the note, update the note | 0 | March | Planning | 14/03/2025 14:34:37 | subtasks
14/03/2025 14:34:37 | Noor saleh | Notpade | Subitems |  | update the note | 0 | March | Planning | 14/03/2025 14:34:32 | subtasks
14/03/2025 14:34:23 | Noor saleh | Notpade | Status |  | Done | 0 | March | Planning | 14/03/2025 14:34:23 | color
10/03/2025 22:28:04 | Noor saleh | chat | Timeline | 2024-11-09 - 2024-11-23 |  | 0 | March | Planning | 10/03/2025 22:28:04 | timerange
10/03/2025 22:28:02 | Noor saleh | package to explain users | Priority | Low |  | 0 | March | Planning | 10/03/2025 22:28:02 | color
10/03/2025 22:28:00 | Noor saleh | chat | Priority | Medium |  | 0 | March | Planning | 10/03/2025 22:28:00 | color
05/04/2025 23:55:17 | Noor saleh | chat | Status | Working on it |  | 0 | March | Planning | 10/03/2025 22:27:57 | color
15/03/2025 15:43:16 | Noor saleh | Translate | Status |  | Working on it | 0 | March | Planning | 10/03/2025 22:27:49 | color
10/03/2025 22:24:04 | Noor saleh | app book reader | Status |  | Done | 0 | March | Planning | 10/03/2025 22:24:04 | color
16/11/2024 20:55:13 | Aya Amjad | package to explain users | Owner | Aya Amjad |  | 0 | November | Planning | 16/11/2024 20:55:13 | multiple-person